

| **NOFO Timeline** |
| --- |
| **Typical Date** | **Action** | **Requirement** | **Notes** |
| **CoC Registration** |
| Second Tuesday in January at 1 PM EST | **CoC Registration Opens** - CoC Applicants required to apply using Program Registration Guidelines provided by HUD.  | Required | 2023 Date: January 10 |
| Late January - March | **Registration Webinar -** HUD may host a webinar outlining CoC Registration instructions.  | Suggested | 2023 Date: N/A2022 Date: March 23 |
| First Thursday of March at 5 PM EST | **CoC Registration Closes** - CoC Applicant notifies HUD intent to apply for funds. If CoC does not complete registration HUD will move the previous year’s registration forward with no changes.  | Required | 2023 Date: March 22022 Date: April 7 |
| **NOFO Project Application** |
| July/August | **NOFO Released/Posted** - The NOFO document is posted to Grants.gov. Competition officially opens.  |  | 2023 Date: July 52022 Date: August 12021 Date: August 18 |
| Early August | **Form Rank and Review Committee -** The CoC Applicant can form a committee that will rank and review project applications. Though suggested, this will contribute towards higher scoring in the NOFO application.  | Suggested  | HUD will award up to 27 points to CoCs that demonstrate the existence of a single coordinated, inclusive, and outcome-oriented community process for the solicitation, objective review, ranking, and selection of project applications. See NOFO, Project Capacity, Review and Ranking, 2a & 2g. |
| Early August | **Bidders Conference/ Gather Applicant Interest/ RFP -** CoC Applicant can hold a conference, solicit project applicants, or publish a Request for Proposals (RFP) to increase knowledge of the CoC Project Application to the community.  | Suggested | See NOFO, Project Capacity, Review and Ranking, 2a & 2g. |
| Mid August | **Post Application for Local Applicants -** CoCs can post the criteria and application requirements online to encourage Project Applicants to apply.  | Suggested | See NOFO, Project Capacity, Review and Ranking, 2a & 2g. |
| Mid August | **E-Snaps Opens for Submission -** HUD’s online application website, E-SNAPS, opens for CoC applicants to submit their CoC Applications.  |  | 2023 Date: July 31 2022 Date: August 16 |
| Mid/Late August | **NOFO Webinar** - CoC applicants can attend the HUD Webinar reviewing current year NOFO changes, requirements and scoring. | Suggested | 2023 Date: August 252022 Date: August 11 |
| Late August | **Project Application Due -**  All community project applications must be submitted to the CoC no later than 30 days before HUD’s CoC Program application submission deadline. | Required | Must be submitted 30 Days prior to Submission Deadline |
| **CoC Project Ranking & Submission** |
| Late August - Mid September | **CoC Project Review and Ranking** - Project applications must be reviewed and ranked, approved and rejected by the CoC. They must be listed on the CoC Priority listing in rank order; higher ranked will be assigned to Tier 1 and lower ranked will be assigned to Tier 2.  | Required |   |
| Mid September | **Notify Project Applicants** - CoC Deadline to Notify all project applicants whether project application will be accepted and ranked on the CoC Priority listing, rejected or reduced by the CoC. | Required | Must be notified 15 Days prior to Submission Deadline |
| Mid September | **Application Decision Appeals -** Community applicants can dispute their ranking.  | Suggested |  |
| 2 Days Prior to Submission Deadline | **Post Consolidated Application** - CoC must post on their website all parts of the CoC Consolidated application and notify community members that the Consolidated application is available to view.  | Required | Must post 2 Days prior to Submission Deadline |
| Late September | **NOFO Submission Due -** The CoC Consolidated application must be uploaded and submitted to E-Snaps. | Required | 2023 Date: September 282022 Date: September 302021 Date: November 16 |
| **HUD Review & Scoring Announcement** |
| Early October through Early January | **HUD Review Period -** HUD will review project applications to determine CoC Award amounts for the CoC Applicants.  |  |  |
| Mid January | **HUD Announces Awards** - HUD will announce the Tier 1 Awards Report to the CoC Applicant.  |  | 2023 (Prior Year) Date: January 14 |
| Late March | **HUD Announces Awards** - HUD will announce the Tier 2 Award Report to the CoC Applicant.  |  | 2023 Date (Prior Year): March 27 |