## Sheet1
Task | Responsible Party | Due Date | Status | Resources | Notes
Plan Your Work Group
Identify transition project team members |  |  | Complete | Roster
Determine team member roles & responsibilities |  |  | In progress | Onboarding Roles & Responsibilities Decision Log
Determine work group meeting structure |  |  | Blocked
Schedule first meeting |  |  | On hold
Plan Your Project and Set Goals
Review legacy system as a group and identify priorities and changes |  |  | Not started |  | Participation: Who does and doesn’t participate in your HMIS. Will that change when you adopt Clarity Human Services? Workflows: What workflows are currently supported in your legacy system? Will these workflows need to be replicated in Clarity? Are improvement or increased efficiency a priority for you? Coordinated Entry: Is coordinated entry integrated into your HMIS? Would you like it to be? Data Quality: What data quality issues exist in your HMIS? What data quality issues do you want to be sure to prevent in your new HMIS? Local Reporting Needs: What critical local reporting needs do you have and how quickly will you need to produce these data from Clarity? Trouble Spots: What challenges do you currently experience with your HMIS? What are you expecting to address by switching to Clarity?
Review coordinated entry, outreach, and inventory functionality & determine if you'll use these features in Clarity |  |  | Not started | Inventory One-Pager Coordinated Entry One-Pager Outreach One-Pager
Request & attend Clarity Human Services product demo for coordinated entry, outreach, or inventory, if applicable |  |  | Not started
Complete goal setting worksheet |  |  | Not started | Goal Setting Worksheet
Determine tentative go-live date |  |  | Not started | Go-Live Calculation Worksheet | Bitfocus recommends setting a go-live date six months after your contract signing date. This provides ample time for planning, training, configuring, formatting, and testing to ensure your transition goes smoothly
Discuss timeline needs for implementation |  |  | Not started |  | All organizations and projects will need to be configured (aka built in the system) in order to migrate the data. However, there are other parts of the system, like assessments and services, that you may want available at your go-live. Determine what pieces you will want to be ready to use at go-live so you can allocate time to configure them. This is also the time to discuss what resources are currently available for implementation, what resources you may need to add for implementation, and what level of support you'll need from Bitfocus.
Identify support needs from Bitfocus |  |  | Not started |  | Available Bitfocus supports include: -Configuration Support -Implementation Support -Training support (including training users or train-the trainer models. Training support is available live or recorded) -Custom data formatting
Engage Your Community
Complete Stakeholder Map |  |  | Not started | Stakeholder Map | Complete stakeholder map to ensure you've accounted for the needs of stakeholders in transition. Consider HMIS users, HMIS administrators, agency leadership, and coordinated entry teams.
Create Communication Plan |  |  | Not started | Communication Plan
Draft initial communications |  |  | Not started | Sample Community Email Sample Community Presentation Sample Press Release
Plan stakeholder engagement meetings |  |  | Not started |  | Stakeholder meetings are intended to provide updates, problem solve, and solicit feedback from highly involved stakeholders
Plan Technology Solutions
Plan user support |  |  | Not started |  | Create procedures for problem resolution an support escalation. Consider how you can provide the following resources to your end users: -A help desk to address day to day user questions and issues -Self-serve support such as the Bitfocus Help Center along with local workflow and policy instructions -Training, including new user training, refresher trainings, role-specific, and topic-specific trainings
Assign key point of contact for providing end user support |  |  | Not started
Determine system sharing |  |  | Not started |  | Determine sharing settings for your system. What will your overall system sharing settings look like? What about agency level? What is currently in your ROI, Privacy Notices, and Client Consent forms?
Review the HUD Migration Elements |  |  | Not started | HUD Migration Elements | Review the HUD Migration Elements to understand what data will be moved during the HUD migration phase. Your Bitfocus Project Manager will review this chart with you again after you kick-off your migration.
Assess your data quality and decide how far back to migrate |  |  | Not started |  | How far back do you need to go when migrating data? Do you know your data retention policy?
Determine what data is critical to have available at go-live and what data can wait |  |  | Not started |  | Some data, like assessments, are not migrated during the HUD mgration phase of onboarding. It's important to determine which historic data is critical to have at go-live and what can wait. Please note, if custom file types need to be migrated concurrently with the HUD migration phase, the black-out period will be extended by several weeks. Bitfocus does not recommend migrating additional data during the HUD migration phase.
Determine which custom file types you will migrate over after the HUD migration |  |  | Not started | HUD & Custom Data Migration Instructions HUD's CSV Specifications | Determine which file types, if any, you'll migrate over after your HUD migration and go-live. Prioritize based on importance. Are you familiar with HUD data standards such that you understand what data is likely to be available at go-live? If not, HUD’s CSV specifications in conjunction with Bitfocus' HUD & Custom Data Migration Instructions can be particularly useful.
Identify agreements that need to be put in place or updated for go-live |  |  | Not started |  | Resources can include releases of information, user agreements, agency agreements, training materials, etc.
Analyze Reporting Needs |  |  | Not started |  | -Compare Clarity Human Services reports with needed reports -Identify which reports are critical -Identify custom reports needed
Plan for your Blackout Period |  |  | Not started |  | Plan strategies for data collection and entry, as well as a communication and training strategy for HMIS users. Your Blackout period will occur between your final HUD csv upload and your go-live date. It is usually a two-week period. Review your community’s HMIS outage policy to determine your procedures for down time
STOP HERE Below, you'll find a sample project plan for the rest of your onboarding and data migration journey. Your Bitfocus project manager will review this plan with you in detail and customize the plan to meet your community's needs. Bitfocus will work closely with you and your project team to ensure everyone understands the tasks listed below, to assign a responsible party of each task, and to ensure you have the materials and support you need to complete the tasks.
Onboarding with Bitfocus
Meet your Bitfocus Project Management Team |  |  | Not started |  | Attend project kick-off call with Professional Services team
Complete training with Bitfocus |  |  | Not started |  | Training content includes the following topics: -General features of Clarity Human Services -How to administer Clarity -How to manage agencies within Clarity -Coordinated entry in Clarity
Determine decision making process for configuration decisions. |  |  | Not started |  | Bitfocus will provide you with a configuration decision guide at the kick-off call. It may also be helpful to rereview the decision log.
Identify short-term improvements you’d like to make in the transition to Clarity, such as merging programs, renaming agencies, or removing out of date reports & assessments. |  |  | Not started |  | This may include implementing standardized naming conventions, moving or merging programs, or changing program structures. The transition is a great opportunity to better organize your system.
Review your current data collection and determine what elements are important to retain. |  |  | Not started |  | All items you choose to migrate will need to be configured.
Configure your new Clarity system. |  |  | Not started |  | Configuration means building in Clarity Human Services. You'll configure, or build, elements in your system by creating them and adjusting their settings. Your Bitfocus project management team will walk through each of the features you'll be configuring and guide you through the decisions you'll need to make about functionality. At a minimum, you'll need to configure agencies, programs, and certain HUD-funded services to prepare for the HUD migration phase. You may need to configure more than just agencies, programs, and certain HUD-funded services if you are planning on using custom services and assessments at go-live. Configuration typically takes most communities about 6 weeks. Among other things, you’ll configure: -Agencies and programs -Services -Privacy and security settings -Access roles Assessments Referral settings
Identify any community preparations or supports that need to be in place for the migration. Set a timeline for them by inserting them in this project plan. |  |  | Not started |  | This includes dates you'll set for training end users, user and agency agreements you'll collect, and any reviews and revisions of privacy agreements and/or HMIS policies and procedures that may be impacted by the transition to Clarity Human Services.
HUD Test Migration Preparation
Upload legacy data in the format specified by your Bitfocus Project Manager |  |  | Not started |  | Your Bitfocus project management team will provide you with a link to upload your legacy data file for the test migration.
Attend migration kick-off call with Data Integrations team to review Data Analysis Report (DAR) |  |  | Not started |  | Your Bitfocus project management team will schedule a meeting with you and the Bitfocus Data Integrations team to review issues with your data and walk through solutions. Bitfocus will apply all solutions to your data for you.
Determine Data Quality Correction Methods and send final decisions to Professional Services team |  |  | Not started |  | There may be outstanding decisions after the DAR meeting. Once you have finalized these choices, let your project management team know.
Complete Test Migration Mapping
Map programs & services for migration (mig) site |  |  | Not started |  | Your Bitfocus project manager will provide you with a mapping document and instructions. This mapping document will be used to ensure data taken from your HUD csv file connects correctly to the programs, agencies, and services you've built in Clarity Human Services
Complete corrections to mapping document |  |  | Not started |  | Your Bitfocus project manager will contact you with any questions or changes needed to the mapping document
Review and sign test Migration Sign-Off Sheet |  |  | Not started |  | Your Bitfocus project manager will provide you with a sign-off sheet that certifies your mapping document is correct, gives Bitfocus permission to run the data correction methods you decided on, and gives Bitfocus permission to run your test HUD data migration in your mig site
Testing Migration Site Data Import
Test Migration Site Data |  |  | Not started |  | You'll spend three weeks testing the data imported to your mig site to ensure the data migrated correctly. Your project manager will review the instructions for migration site data testing and provide you with a spreadsheet to report any findings. Your project manager and the Bitfocus team will work with you in real time to address and solve data migration findings to ensure they are not replicated in the live site migration. Be prepared to run one APR or CAPER for each project type at each agency configured in your system.
Confirm data is ready to go |  |  | Not started |  | When you have completed testing, let your project manager know so that the live migration process may begin.
Continue to get your end users and community ready for go-live |  |  | Not started |  | The test migration period is a good time to continue to get your community ready for go-live. This includes scheduling and conducting end-user training, collecting user and agency agreements, updating policies and procedures, and communicating your black-out period data collection strategy.
HUD Live Migration Preparation
Upload final legacy data in the format specified by your Bitfocus Project Manager |  |  | Not started |  | Your blackout period will begin as soon as you dowload this final legacy file. The file will be due at 9 AM PT on a date scheduled with your project manager. To minimize your blackout period impact, dowload the file close to the due date and time
Review final DAR & data correction methods |  |  | Not started |  | The final DAR should be similar to the test DAR. If there are any new major or minor issues outside of those you've already agreed upon solutions to, you will be notified by your project manager. Otherwise, the same data quality correction methods from the test migration will be applied to the final migration.
Complete Final HUD Migration Mapping
Map programs & services for live site |  |  | Not started |  | This is the same pricess you completed during the test migration, but you will use information from your live site to complete the spreadsheet rather than from your test site
Complete corrections to mapping document |  |  | Not started |  | Your Bitfocus project manager will contact you with any questions or changes needed to the mapping document
Review and sign final Migration Sign-Off Sheet |  |  | Not started |  | Your Bitfocus project manager will provide you with a sign-off sheet that certifies your mapping document is correct, gives Bitfocus permission to run the data correction methods you decided on, and gives Bitfocus permission to run your final HUD data migration in your live site
Testing Live Site Data Import
Go-Live |  |  | Not started |  | Once Bitfocus completes your data migration, your balckout period ends and your go-live period begins. Some customers choose to go live and give users access immediately. Some prefer to test the data for a short period prior to opening the system up to HMIS users. Determine which method you will use and announce your go-live!
Test Live Site Data |  |  | Not started |  | You have 30 days to review your live site data and report any issues to your project manager. Your project manager will work with you and the Bitfocus team to resolve these issues in real time.